## Summary
SRD Logistics Dashboard Enhancement - Effort Summary
Option A: Streamlit/Python (incl. data layer) | Best case | Estimated | Worst case
Base effort (hours)
Contingency buffer (hours)
Total with buffer (hours)
Working days
Calendar weeks
Cost (INR)
Option B: Power BI on PostgreSQL DWH (client provides data up to DWH)
Metric | Best case | Estimated | Worst case
Base effort (hours)
Contingency buffer (hours)
Total with buffer (hours)
Working days
Calendar weeks
Cost (INR)
Difference: Option B vs Option A (total hours, estimated)
Sheets: Effort Estimate (Option A) ¦ Power BI Estimate (Option B) ¦ Requirement Mapping ¦ Assumptions.
Cost is 0 until a rate is entered in Assumptions!B7.

## Power BI Estimate
SRD Logistics - Power BI Delivery (Pentaho ETL -> PostgreSQL DWH -> Power BI)
Scope: data already loaded to DWH facts & dimensions by client. Blue = input hours, black = formula.
# | Work package | Requirement section(s) | Scope in Power BI architecture | Best case (h) | Estimated (h) | Worst case (h) | % of base
1 | Discovery & clarification | All | Report definitions, review of DWH schema (facts/dims), definitions of service %, via, KT weight | 10 | 12 | 18
2 | Semantic model | 0, 9 | PostgreSQL connection, relationships, date dimension, security, model performance | 18 | 24 | 32
3 | Configurable target engine | 1, 9 | Target table in DWH, what-if / field parameters for target days (4/5/6/7+), DAX measures | 16 | 20 | 28
4 | Service % & target achievement reports | 1, 2 | Source/destination/route/via/business service %, target %, actual %, variation %, ranking | 24 | 30 | 40
5 | Delay & journey analysis, drill-through | 3 | Stage-wise delay, route -> stage -> LR -> reason drill-through, remarks | 24 | 30 | 40
6 | LR search & consignor/consignee analytics | 4 | LR journey page, consignor/consignee reports and variation vs target | 16 | 20 | 28
7 | Period-wise & comparison reports | 5 | Weekly/10-day/15-day/monthly/yearly, custom period, current vs previous (DAX time intelligence) | 10 | 14 | 20
8 | Booking -> main hub dispatch | 6 | Receipt/dispatch times, pending/delayed/dispatched LR ageing, source & hub performance | 18 | 22 | 30
9 | Live reports | 7 | DirectQuery or near-real-time refresh on DWH (Pentaho pulls SRD API); 6 live reports | 18 | 24 | 40
10 | Improvement suggestions | 8 | SQL/Python job writing route/stage/LR suggestions to DWH; surfaced in Power BI | 12 | 16 | 24
11 | ML delay-risk scoring (optional) | Existing | Python scoring job writes risk & top factors to DWH; Power BI reads. Drop if not required | 14 | 20 | 28
12 | Slicers, filters & export | 9 | Slicers for period/source/destination/via/business/consignor/consignee/LR, export | 6 | 8 | 12
13 | Testing, UAT, gateway, refresh, publish | All | UAT cycle, on-prem gateway, scheduled refresh, Power BI Service deployment, documentation | 18 | 24 | 32
Base total (before buffer)
| Contingency buffer |  | Linked to Assumptions!B3 (same 100 h buffer)
GRAND TOTAL (with buffer)
Assumptions
1. Data engineering (Pentaho ETL, staging, PostgreSQL DWH facts/dimensions) is done by the client and excluded.
2. DWH already contains LR, consignor, consignee, via, hub, business and journey-stage timestamps; otherwise ETL effort returns.
3. Power BI cannot run the scikit-learn/SHAP model directly; ML is a Python scoring job writing to the DWH (row 11, optional).
4. Live API data is pulled by Pentaho into the DWH every few minutes; Power BI uses DirectQuery. Streaming datasets would change effort.
5. Excluded: Power BI Pro/Premium licensing, hosting, user management beyond basic row-level security.
6. Best/worst case columns are judgement-based ranges around the estimate, not statistical bounds.

## Effort Estimate
SRD Logistics - Service Performance & Live Reporting: Effort Estimate
Blue = editable input hours. Black = formula. Yellow = key assumption.
# | Work package | Requirement section(s) | Scope / what changes in existing app | Best case (h) | Estimated (h) | Worst case (h) | % of base
1 | Discovery & clarification | All | Requirement clarification, SRD data & API mapping, definitions (service %, via, KT weight) | 16 | 20 | 28
2 | Data layer (real SRD data) | 0 | Ingestion/ETL, LR-level schema (LR, consignor, consignee, via, hub, business, stage timestamps), cleaning & validation | 30 | 40 | 55
3 | Configurable target engine | 1, 9 | Per route / source-destination benchmark TAT, target-days (4/5/6/7+), config UI, no hard-coded rules | 22 | 28 | 36
4 | Service % & target achievement reports | 1, 2 | Source/destination/route/via/business service %, target %, actual %, variation %, ranked delays | 26 | 32 | 42
5 | Delay & journey analysis + drill-down | 3 | Stage-level delay logic (booking→delivery), route→stage→LR→reason drill-down, delay remarks | 30 | 36 | 46
6 | LR search, consignor/consignee analytics | 4 | LR journey timeline, consignor/consignee search & service % vs target, source/dest/route/period drill-down | 22 | 28 | 36
7 | Period-wise & comparison reports | 5 | Weekly/10-day/15-day/monthly/yearly views, custom period, current vs previous comparison | 16 | 20 | 26
8 | Booking → main hub dispatch | 6 | Receipt/dispatch time calc, pending/delayed/dispatched LR ageing, source & hub performance | 22 | 28 | 36
9 | Live reports via SRD API | 7 | API client/auth, polling & caching, 6 live reports (bookings, lag/lead, target, KT weight, godown stock, hub movement) | 28 | 36 | 56
10 | Improvement suggestions engine | 8 | Move rule engine from network level to route/stage/LR-level suggestions | 16 | 20 | 26
11 | ML retraining & explainability | Existing | Retrain on real data, update features, SHAP & what-if adjustments | 14 | 20 | 28
12 | Global filters & export | 9 | Filters for via/business/consignor/consignee/LR, CSV/Excel export, standard report table | 10 | 12 | 16
13 | Testing, UAT fixes, deployment, docs | All | Unit tests, UAT cycle, deployment, user documentation | 24 | 30 | 40
Base total (before buffer)
| Contingency buffer (requested) |  | Additional buffer agreed with stakeholder; covers unknown data quality, API spec, UAT rework, scope creep
GRAND TOTAL (with buffer)

## Assumptions
Assumptions & Inputs
Parameter | Value | Note
Contingency buffer (hours) | 100 | Requested by user: additional 100 h on top of base estimate
Working hours per day | 8 | Assumed
Working hours per person-week | 40 | Assumed
Team size (developers) | 1 | Assumed single full-time developer; change to see duration
Blended hourly rate (INR) | 0 | Not provided - enter rate to compute cost
Key assumptions and risks
1. Real SRD LR-level data is provided; if not, a new synthetic generator is needed (~30 h extra, covered by buffer).
2. SRD live API is documented with endpoints, auth and rate limits; 'live' = periodic polling in Streamlit, not streaming.
3. Data volume stays near current scale (~120k records); larger volumes need caching/DB layer (~20 h, covered by buffer).
4. Ambiguous terms to confirm with client: 'KT weight', exact service % definition, meaning of 'via'.
5. Excluded: hosting/DevOps, user login/role management, mobile layouts.
6. Based on review of the existing repo: 14-page Streamlit app, shipment-level synthetic data, no LR/consignor/consignee/via/business concept, fixed promised-days target.
7. Source of requirements: SRD Logistics Consolidated Service Performance & Live Reporting Requirements (3-page scanned PDF with handwritten notes).

## Requirement Mapping
Section | Requirement | Current app status | Gap / update needed | Work package #
1 | Service % (overall, source, destination, route) vs target, variation | Partly available (route delay/on-time %) | Configurable target %, actual vs target, variation; target-days filter | 3, 4
1 | Consignor / consignee service % vs target | Missing | New entity and reports | 6
2 | Source-to-destination, source, destination, via, business performance | Partly (route, warehouse) | Add via and business views, ranking highest→lowest | 4
3 | Delay reason & % at each journey point; booking→delivery analysis | Partly (component times, delay reason) | Stage-level logic and 4-level drill-down with remarks | 5
4 | Search LR, full journey; consignor/consignee search & variation | Missing | LR timeline page; customer drill-down | 6
5 | Weekly/10-day/15-day/monthly/yearly; period comparison | Missing (date range filter only) | Period engine and comparison dashboard | 7
6 | Booking → main hub dispatch, ageing, pending LRs | Missing | New page with hub timestamps and ageing buckets | 8
7 | Live reports using SRD APIs (bookings, lag/lead, target, KT weight, godown stock, hub dispatch) | Missing | API integration and 6 live reports | 9
8 | System-generated route/stage/LR improvement suggestions | Partly (network-level rules) | Route/stage/LR-level suggestions | 10
9 | Filters (period, source, destination, via, business, consignor, consignee, LR, target days), configurable rules, export | Partly (10 filters) | Add new filters, config screen, standard report table, export | 3, 12
Existing | ML risk prediction, SHAP, what-if | Available (synthetic data) | Retrain on real data | 11